## Screens
Appendix 2. Idaho Department of Fish and Game — Anadromous Fish Screen Program
BPA project number | Site name | Screen type | Screen size range (CFS) | Maintenance responsibility | Year Built / Date Screened | Partners | Subbasin | Operational compliance with state and Federal criteria? | Comments | Non-recurring maintenance required in near future at existing active screens | Estimated cost of non-recurring expense | Estimated schedule for non-recurring maintenance | Estimated cost of normal weekly maintenance | Latitude | Longitude | Maintenance priority italic = consider for action (10 screens), bold = short list for repair (35 screens)
1994-015-00 | L-03AO | Rotary Drum | 15 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, relocate new screen and bypass | new screen /bypass | 100000 | 2018 | 90 | 45.1608 | -113.8329 | 1
1994-015-00 | L-06 | Rotary Drum | 52 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes | Add debris rack + bypass relacement | new bypass | 7500 | 2018 | 140 | 45.1292 | -113.7972 | 2
1994-015-00 | L-08 | Rotary Drum | 8 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 60000 | 2018 | 70 | 45.1204 | -113.7796 | 3
1994-015-00 | L-10 | Rotary Drum | 33 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes | Replacement 2018 | new screen considered | 175000 | 2018 | 100 | 45.1056 | -113.7389 | 4
1994-015-00 | L-14 | Rotary Drum | 15 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | possible consolidation with L-15 | 95000 | 2-5 years | 90 | 45.0892 | -113.7213 | 5
1994-015-00 | L-15 | Rotary Drum | 18 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | possible consolidation with L-14 | 100000 | 2-5 years | 90 | 45.08 | -113.7159 | 6
1994-015-00 | L-16/17 | Rotary Drum | 18 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 100000 | 2019 | 90 | 45.0704 | -113.7056 | 7
1994-015-00 | L-20 | Rotary Drum | 24 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 130000 | 2019 | 90 | 45.0465 | -113.6788 | 8
1994-015-00 | L-21 | Rotary Drum | 15 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 90000 | 2-5 years | 90 | 45.0415 | -113.6763 | 9
1994-015-00 | L-26 | Rotary Drum | 5 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 27000 | 2-5 years | 70 | 45.0093 | -113.6568 | 10
1994-015-00 | L-28 | Rotary Drum | 12 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 80000 | 2-5 years | 90 | 44.9875 | -113.6496 | 11
1994-015-00 | L-43 | Rotary Drum | 7 | IDFG | 2000 | BPA, NMFS, IDFG | Lemhi River | non-criteria pump | unused screen - remove? / build pump screen | new pump | 30000 | 2-5 years | 70 | 44.854 | -113.6164 | 12
1994-015-00 | L-44 | Rotary Drum | 6 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 35000 | 2-5 years | 70 | 44.8309 | -113.6108 | 13
1994-015-00 | L-45 | Rotary Drum | 8 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen/ needs access possible consolidate with L-43C site | new screen and access | 40000 | 2019 | 70 | 44.8302 | -113.611 | 14
1994-015-00 | L-45A | Rotary Drum | 8 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 37000 | 2-8 years | 70 | 44.8152 | -113.5803 | 15
1994-015-00 | L-45B | Rotary Drum | 6 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 30000 | 2-3 years | 70 | 44.8091 | -113.5737 | 16
1994-015-00 | L-45C/D | Rotary Drum | 33 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes | bridge replacement needed | bridge repair | 50000 | 2020 | 100 | 44.8063 | -113.567 | 17
1994-015-00 | L-48/49 | Rotary Drum | 39 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes | bypass design problem | new bypass | 10000 | 2019 | 100 | 44.7801 | -113.5419 | 18
1994-015-00 | L-51 | Rotary Drum | 6 | IDFG | 1992 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 30000 | 3-4 years | 70 | 44.7669 | -113.7066 | 19
1994-015-00 | L-58B | Rotary Drum | 15 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 90000 | 2-5 years | 90 | 44.7363 | -113.4483 | 20
1994-015-00 | L-58C | Rotary Drum | 12 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 70000 | 2-5 years | 90 | 44.7305 | -113.4371 | 21
1994-015-00 | L-59 | Rotary Drum | 8 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 40000 | 2-5 years | 70 | 44.7276 | -113.4214 | 22
1994-015-00 | L-60 | Rotary Drum | 7 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | new screen | 37000 | 2-5 years | 70 | 44.7191 | -113.4112 | 23
1994-015-00 | L-61 | Rotary Drum | 11 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes | install larger drums/ excavation/rock work | new screen | 65000 | 2017 | 90 | 44.7154 | -113.4048 | 24
2007-399-00 | L-62A PUMP | POD Drum | 5 | IDFG | 2011 | BPA, NMFS, IDFG | Lemhi River | yes | bottlebrush | replace pipe to pump | 5000 | 2017 | 90 | 44.6887 | -113.3647 | 25
1994-015-00 | LBSC-05 | Rotary Drum | 15 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | Older 45° screen, 20 years or older | may need rebuild | 90000 | 2-5 years | 90 | 44.712 | -113.4112 | 26
1994-015-00 | LBSC-05A | Rotary Drum | 4 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep needs bypass repair at screen +bridge would prevent creek crossing | repair bypass | 3000 | 2-5 years | 70 | 44.7124 | -113.4087 | 27
1994-015-00 | P-08 | Rotary Drum | 15 | IDFG | 1994 | BPA, NMFS, IDFG | Pahsimeroi River | yes | new screen needed - bypass backflow | new screen | 90000 | 2-5 years | 90 | 44.6188 | -113.9851 | 28
2007-399-00 | P-10 | Rotary Drum | 4 | IDFG | 2015 | BPA, NMFS, IDFG | Pahsimeroi River | yes | new screen needed - obsolete | new screen | 28000 | 2016 | 70 | 44.5894 | -113.9467 | 29
1994-015-00 | S-02 | Rotary Drum | 5 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep blowoff bypass no good | HG blowoff ditch needed | 10000 | 2-5 years | 70 | 45.3652 | -113.9645 | 30
1994-015-00 | S-08 | Rotary Drum | 4 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep may change to pump system - no headgate control bypass backflow | new pump station | 27000 | 2-5 years | 70 | 45.2302 | -113.8879 | 31
1994-015-00 | S-23A | Rotary Drum | 5 | IDFG | 1990 | BPA, NMFS, IDFG | Upper Salmon River | no | need new screen and bypass + diversion | new screen | 27000 | 2017 | 70 | 44.5951 | -114.1878 | 32
1994-015-00 | S-28 | Rotary Drum | 208 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes | problem with bypass structure | repair bypass | 4000 | 1-2 years | 153 | 44.4586 | -114.2222 | 33
1994-015-00 | SChaC-01 | Vertical Flat Plate | 4 | IDFG | 2005 | BPA, NMFS, IDFG | Upper Salmon River | yes | remove and replace | restore | 28000 | 5-10 years | 70 | 44.5693 | -114.1943 | 34
2007-399-00 | SEF-13 | Rotary Drum | 8 | IDFG | 2011 | BPA, NMFS, IDFG | East Fork Salmon River | yes | Access - needs new overflow control structure | head gate spill structure | 22000 | 1 -3 years | 70 | 44.1456 | -114.3902 | 35
1994-015-00 | SEF-15 | Vertical Flat Plate | 17 | IDFG | 2006 | BPA, NMFS, IDFG | East Fork Salmon River | no | Needs Replaced |  | 95000 | 2-5 years | 90 | 44.1306 | -114.4185 | 36
1994-015-00 | SEF-16 | Rotary Drum | 9 | IDFG | 1984 | BPA, NMFS, IDFG | East Fork Salmon River | no | new screen and bypass needed | new screen | 70000 | 1 -3 years | 70 | 44.1241 | -114.4221 | 37
1994-015-00 | SIC-07 | Rotary Drum | 18 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes | new footbridge / reduction of bays | reduce bays | 7000 | 1 -3 years | 90 | 44.9103 | -114.0371 | 38
1994-015-00 | SMC-07 | POD Drum | 3 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes | remove and replace | restore | 25000 | 2018 | 70 | 44.6277 | -114.1903 | 39
1994-015-00 | SNF-01 | Rotary Drum | 8 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes |  | new screen | 37000 | 2-5 years | 70 | 45.4175 | -113.9943 | 40
1994-015-00 | SNF-02A | Rotary Drum | 2 | IDFG | 1993 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep | new screen | 17000 | 5-10 years | 70 | 45.4243 | -113.994 | 41
1994-015-00 | SNF-07A | Rotary Drum | 4 | IDFG | 1994 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep bridge | new screen | 26000 | 5-10 years | 70 | 45.499 | -113.9646 | 42
2007-399-00 | SOC-01 | POD Drum | 2 | IDFG | 2010 | BPA, NMFS, IDFG | Upper Salmon River | yes | bottlebrush -inactive -buried under silt | dig out- repair | 25000 | 2017 | 70 | 45.3235 | -114.4523 | 43
1994-015-00 | SPC-01 | Rotary Drum | 15 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | New Screen | new screen/headgate | 160000 | 2015 | 90 | 43.9096 | -114.7579 | 44
1994-015-00 | SSC-03 | Rotary Drum | 5 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep terrible velocities | new screen or pipe configure | 25000 | 2-5 years | 70 | 44.2901 | -114.4592 | 45
1994-015-00 | L-02 | Rotary Drum | 6.12 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 45.1715 | -113.871
1994-015-00 | L-03 | Rotary Drum | 33.28 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes | problem at blowoff |  |  |  | 100 | 45.1613 | -113.8419
1994-015-00 | L-03A | Rotary Drum | 22.19 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 45.1529 | -113.8144
1994-015-00 | L-07 | Rotary Drum | 42.84 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes | add debris rack |  |  |  | 140 | 45.1221 | -113.7875
1994-015-00 | L-08A | Rotary Drum | 33.28 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 45.1143 | -113.7528
1994-015-00 | L-09 | Rotary Drum | 27.54 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes | difficulties with siphon |  |  |  | 100 | 45.1137 | -113.7705
1994-015-00 | L-13 | Rotary Drum | 27.73 | IDFG | 2003 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 45.0944 | -113.8929
1994-015-00 | L-19 | Rotary Drum | 9.24 | IDFG | 1999 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 45.0556 | -113.6896
1994-015-00 | L-22 | Rotary Drum | 27.54 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 45.0382 | -113.6732
1994-015-00 | L-22A/23 | Rotary Drum | 27.73 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 45.0347 | -113.6659
1994-015-00 | L-24 | Rotary Drum | 6.12 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes | bypass outflow blockage |  |  |  | 70 | 45.0131 | -113.6579
1994-015-00 | L-25 | Rotary Drum | 15.3 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 45.0126 | -113.658
1994-015-00 | L-27 | Rotary Drum | 7.65 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | 45° | screens twenty years or older |  |  |  | 70 | 44.9932 | -113.6528
1994-015-00 | L-29 | Rotary Drum | 27.54 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.9834 | -113.6461
1994-015-00 | L-30 | Rotary Drum | 44.37 | IDFG | 2000 | BPA, NMFS, IDFG | Lemhi River | elevated bypass | elevated bypass inlet |  |  |  | 140 | 44.9687 | -113.6471
1994-015-00 | L-30A | Rotary Drum | 7.4 | IDFG | 2001 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.9562 | -113.6436
1994-015-00 | L-31 | Rotary Drum | 18.36 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.9592 | -113.6429
1994-015-00 | L-31A | Rotary Drum | 22.95 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.9274 | -113.9071
1994-015-00 | L-31B | Rotary Drum | 3.57 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.9433 | -113.6412
1994-015-00 | L-32 | Rotary Drum | 27.54 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | 45° | screens twenty years or older |  |  |  | 100 | 44.9222 | -113.9027
1994-015-00 | L-33 | Rotary Drum | 27.73 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | bypass issue | address bypass problem |  |  |  | 100 | 44.9207 | -113.9044
1994-015-00 | L-34 | Rotary Drum | 2.3 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.9169 | -113.6295
1994-015-00 | L-35 | Rotary Drum | 3.57 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.9123 | -113.6286
1994-015-00 | L-35A | Rotary Drum | 6.12 | IDFG | 2003 | BPA, NMFS, IDFG | Lemhi River | velocity problems | POD screen with design problems |  |  |  | 70 | 44.912 | -113.6255
1994-015-00 | L-36/37 | Rotary Drum | 7.4 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | elevated bypass | bypass inlet height / gear change? |  |  |  | 70 | 44.9001 | -113.6283
1994-015-00 | L-38 | Rotary Drum | 3.57 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.8903 | -113.6267
1994-015-00 | L-39 | Rotary Drum | 4.46 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.8825 | -113.629
1994-015-00 | L-40 | Rotary Drum | 12.24 | IDFG | 1998 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 44.8751 | -113.6283
1994-015-00 | L-41/42 | Rotary Drum | 33.28 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.87 | -113.6253
1994-015-00 | L-43A | Rotary Drum | 7.4 | IDFG | 2001 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.871 | -113.6197
1994-015-00 | L-43B | Rotary Drum | 7.4 | IDFG | 2001 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.8463 | -113.6193
1994-015-00 | L-46/46A | Rotary Drum | 27.73 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.7962 | -113.5606
1994-015-00 | L-47 | Rotary Drum | 33.28 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.7813 | -113.5481
1994-015-00 | L-51A | Rotary Drum | 6.12 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | 45° | screens twenty years or older |  |  |  | 70 | 44.7627 | -113.7014
1994-015-00 | L-53/57 | Rotary Drum | 4.59 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.749 | -113.4746
1994-015-00 | L-58 | Rotary Drum | 9.18 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.7485 | -113.4767
2007-99-00 | L-61B PUMP | POD Drum | 3.75 | IDFG | 2010 | BPA, NMFS, IDFG | Lemhi River | yes | bottle brush |  |  |  | 90 | 44.7011 | -113.3836
1994-015-00 | L-62 | Rotary Drum | 14.79 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 44.7008 | -113.3821
1994-015-00 | LBC-03 | Rotary Drum | 12.94 | IDFG | 2005 | BPA, NMFS, IDFG | Lemhi River | yes | drop well |  |  |  | 70 | 45.1218 | -113.7332
1994-015-00 | LBC-04 | Rotary Drum | 9.18 | IDFG | 2005 | BPA, NMFS, IDFG | Lemhi River | yes | drop well |  |  |  | 70 | 45.1325 | -113.7236
1994-015-00 | LBC-05 | Rotary Drum | 6.12 | IDFG | 2005 | BPA, NMFS, IDFG | Lemhi River | yes | drop well |  |  |  | 70 | 45.1352 | -113.7191
2007-399-00 | LBC-06 | Rotary Drum | 9.24 | IDFG | 2006 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 45.1421 | -113.7139
2007-399-00 | LBC-07 | Rotary Drum | 6.12 | IDFG | 2011 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 45.1674 | -113.7104
2007-399-00 | LBC-09 | Rotary Drum | 8 | IDFG | 2012 | BPA, NMFS, IDFG | Lemhi River | yes | drop well |  |  |  | 70 | 45.1798 | _113.70397
1994-015-00 | LBSC-01 | Rotary Drum | 7.65 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.7228 | -113.4284
1994-015-00 | LBSC-02 | Rotary Drum | 9.18 | IDFG | 1993 | BPA, NMFS, IDFG | Lemhi River | 45° | screens twenty years or older |  |  |  | 70 | 44.7244 | -113.4256
1994-015-00 | LBSC-03 | Rotary Drum | 6.12 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.7152 | -113.4146
1994-015-00 | LBSC-04 | Rotary Drum | 4.59 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes | bridge would prevent creek crossing |  |  |  | 70 | 44.7157 | -113.4136
1994-015-00 | LBSC-06 | Rotary Drum | 9.24 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.7034 | -113.3915
2007-399-00 | LHawC-03 | Rotary Drum |  | IDFG | 2014 | BPA, NMFS, IDFG | Lemhi River | yes
1994-015-00 | LHC-01 | Rotary Drum | 6.12 | IDFG | 1994 | BPA, NMFS, IDFG | Lemhi River | 45° | screens twenty years or older |  |  |  | 70 | 44.8677 | -113.6278
1994-015-00 | LHC-03 | Rotary Drum | 15.3 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 44.8526 | -113.6428
1994-015-00 | LHC-04/06/07 | Rotary Drum | 18.36 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 44.8408 | -113.659
1994-015-00 | LHC-05 | Rotary Drum | 7.4 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.8425 | -113.6571
2007-399-00 | LHC-08 | Rotary Drum | 7.65 | IDFG | 2014 | BPA, NMFS, IDFG | Lemhi River | yes | recently replaced - needs bypass exam |  |  |  | 70 | 44.8305 | -113.6742
1994-015-00 | LHC-08B | Rotary Drum | 4.59 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 70 | 44.813 | -113.687
1994-015-00 | LHC-09 | Rotary Drum | 14.79 | IDFG | 1997 | BPA, NMFS, IDFG | Lemhi River | yes | installed newer bridge / access? |  |  |  | 90 | 44.8045 | -113.6913
1994-015-00 | LHC-10 | Rotary Drum | 15.3 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes | installed newer bridge |  |  |  | 90 | 44.798 | -113.6968
1994-015-00 | LHC-11 | Rotary Drum | 22.95 | IDFG | 1996 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 100 | 44.7976 | -113.6955
1994-015-00 | LHCEF-01 | Rotary Drum | 9.69 | IDFG | 2001 | BPA, NMFS, IDFG | Lemhi River | yes | access road & bypass improvement |  |  |  | 90 | 44.7585 | -113.7099
1994-015-00 | LHC-HATCH | Rotary Drum | 2.3 | IDFG | 1995 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.838 | -113.6908
1994-015-00 | LKC-02 | Rotary Drum | 11.09 | IDFG | 2006 | BPA, NMFS, IDFG | Lemhi River | yes | flow measure/gage at POD |  |  |  | 70 | 45.0318 | -113.6435
1994-015-00 | LKC-03 | Rotary Drum | 3 | IDFG | 2005 | BPA, NMFS, IDFG | Lemhi River | yes | bottle brush |  |  |  | 90 | 45.0456 | -113.6146
1994-015-00 | LS-01 | Rotary Drum | 18.49 | IDFG | 1999 | BPA, NMFS, IDFG | Lemhi River | yes |  |  |  |  | 90 | 45.3957 | -116.3345
1994-015-00 | LSC-02 | Rotary Drum | 3.57 | IDFG | 2002 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.0799 | -113.7044
1994-015-00 | LSRR-01 | Rotary Drum | 2.68 | IDFG | 1999 | BPA, NMFS, IDFG | Little Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.3696 | -116.3679
1994-015-00 | LSRR-02 | Rotary Drum | 3.57 | IDFG | 1999 | BPA, NMFS, IDFG | Little Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.3661 | -116.3735
1994-015-00 | LSRR-03 | Rotary Drum | 6.12 | IDFG | 2004 | BPA, NMFS, IDFG | Little Salmon River | yes |  |  |  |  | 70 | 45.359 | -116.3876
1994-015-00 | LSRRSC-01 | Rotary Drum | 3.57 | IDFG | 2006 | BPA, NMFS, IDFG | Little Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.3558 | -116.3908
1994-015-00 | LWC-01 | Rotary Drum | 4 | IDFG | 2006 | BPA, NMFS, IDFG | Lemhi River | yes | modular |  |  |  | 70 | 45.0994 | -113.7186
1994-015-00 | LWC-02 | Rotary Drum | 3.57 | IDFG | 2006 | BPA, NMFS, IDFG | Lemhi River | yes | check bypass fall |  |  |  | 70 | 45.099 | -113.719
2007-399-00 | LWC-03 | Rotary Drum | 2.3 | IDFG | 2011 | BPA, NMFS, IDFG | Lemhi River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.1023 | -113.7095
2007-399-00 | LWC-04 | Rotary Drum | 4.85 | IDFG | 2007 | BPA, NMFS, IDFG | Lemhi River | yes | modular |  |  |  | 70 | 45.1037 | -113.7079
2007-399-00 | LWC-05 | Rotary Drum | 4.85 | IDFG | 2007 | BPA, NMFS, IDFG | Lemhi River | yes | modular |  |  |  | 70 | 45.1059 | -113.7015
1994-015-00 | P-01A | Rotary Drum | 3.9 | IDFG | 2005 | BPA, NMFS, IDFG | Pahsimeroi River | yes | irrigator maintains flat plate modular solar |  |  |  | 70 | 44.6791 | -114.0368
1994-015-00 | P-02-3 | Rotary Drum | 9.24 | IDFG | 1996 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 70 | 44.6645 | -114.0302
1994-015-00 | P-04 | Rotary Drum | 9.18 | IDFG | 1996 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 90 | 44.6562 | -114.0229
1994-015-00 | P-05 | Rotary Drum | 22.95 | IDFG | 1999 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  | rebuilding drums |  | 2015 | 100 | 44.6515 | -114.021
1994-015-00 | P-06 | Rotary Drum | 14.79 | IDFG | 1997 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 90 | 44.652 | -114.0118
1994-015-00 | P-07 | Rotary Drum | 18.36 | IDFG | 1996 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 100 | 44.6408 | -114.006
2007-399-00 | P-09 PUMP | Rotary Drum | n/a | IDFG | 2008 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 90 | 44.6186 | -113.9794
1994-015-00 | P-12 | Rotary Drum | 9.24 | IDFG | 2004 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 70 | 44.5677 | -113.9222
1994-015-00 | PBSC-01 | Rotary Drum | 27.54 | IDFG | 1996 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 100 | 44.6098 | -113.9593
1994-015-00 | PBSC-02 | Rotary Drum | 14.79 | IDFG | 1996 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 90 | 44.6074 | -113.9495
1994-015-00 | PBSC-03 | Rotary Drum | 27.54 | IDFG | 2002 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 100 | 44.5953 | -113.9371
1994-015-00 | PBSC-04 | Rotary Drum | 7.4 | IDFG | 2003 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 70 | 44.5715 | -113.9111
1994-015-00 | PBSC-06 | Rotary Drum | 4 | IDFG | 2003 | BPA, NMFS, IDFG | Pahsimeroi River | yes |  |  |  |  | 70 | 44.591 | -113.8987
1994-015-00 | PBSC-07/08 | Rotary Drum | 27.73 | IDFG | 2003 | BPA, NMFS, IDFG | Pahsimeroi River | yes | fix bypass ditch outflow | bypass outlet improvement |  |  | 100 | 44.5627 | -113.8901
1994-015-00 | PHatch-01 | Rotary Drum | 44.37 | IDFG | 1994 | BPA, NMFS, IDFG | Pahsimeroi River | 45 | Idaho Power expense |  |  |  | 140 | 44.6825 | -114.0382
1994-015-00 | PHatch-02 | Rotary Drum | 18.49 | IDFG | 1994 | BPA, NMFS, IDFG | Pahsimeroi River | 45 | Idaho Power expense |  |  |  | 90 | 44.5583 | -113.9108
2007-399-00 | PSC-01 | Rotary Drum | 5 | IDFG | 2013 | BPA, NMFS, IDFG | Pahsimeroi River | yes | bottle brush to bubbler |  |  |  | 70 | 44.5583 | -113.9108
1994-015-00 | S-03 | Rotary Drum | 2.87 | IDFG | 1995 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.3383 | -113.9291
1994-015-00 | S-04A | Rotary Drum | 4.46 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.2645 | -113.9009
1994-015-00 | S-05/06/07 | Rotary Drum | 38.82 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | bypass | elevated bypass inlet |  |  |  | 100 | 45.2492 | -113.8979
1994-015-00 | S-09 | Rotary Drum | 60.69 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes | major annual diversion ditch clean |  |  |  | 140 | 45.246 | -113.8929
1994-015-00 | S-10 | Rotary Drum | 60.69 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes | silt problem |  |  |  | 140 | 45.1858 | -113.8936
1994-015-00 | S-11 | Rotary Drum | 60.69 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 140 | 45.1053 | -113.8944
1994-015-00 | S-12 | Rotary Drum | 32.13 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes | vegetation problem - shade solution? |  |  |  | 100 | 45.1045 | -113.8937
1994-015-00 | S-13/14 | Rotary Drum | 118.32 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 153 | 45.0897 | -113.8956
1994-015-00 | S-15 | Rotary Drum | 15.3 | IDFG | 1995 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 45.0812 | -113.9018
1994-015-00 | S-16 | Rotary Drum | 38.82 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | needs Williams Creek siphon |  |  |  | 100 | 45.0383 | -113.9204
1994-015-00 | S-17 | Rotary Drum | 9.24 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 45.0176 | -113.9328
1994-015-00 | S-22 | Rotary Drum | 18.36 | IDFG | 1996 | BPA, NMFS, IDFG | Upper Salmon River | yes | actually runs Morgan Ck flows - silt |  |  |  | 100 | 44.6116 | -114.1689
1994-015-00 | S-23 | Rotary Drum | 15.3 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 44.6002 | -114.1815
1994-015-00 | S-32 | Rotary Drum | 173.4 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 153 | 44.4316 | -114.22
1994-015-00 | S-33 | Rotary Drum | 9.24 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.3871 | -114.2603
1994-015-00 | S-33A | Rotary Drum | 12.11 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | limited access |  |  |  | 90 | 44.3603 | -114.2671
1994-015-00 | S-35 | Rotary Drum | 27.54 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 100 | 44.2876 | -114.303
1994-015-00 | S-39 | Rotary Drum | 22.19 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 100 | 44.1949 | -114.9316
1994-015-00 | S-39A | Rotary Drum | 33.28 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 100 | 44.1848 | -114.9258
1994-015-00 | S-40 | Rotary Drum | 27.73 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes | bad concrete -repair |  |  |  | 100 | 44.06 | -114.8456
1994-015-00 | S-41 | Rotary Drum | 33.28 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 100 | 44.054 | -114.8399
1994-015-00 | S-41 BD | Rotary Drum | 6.12 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | n/a | backdoor from Williams Ck/S-41 |  |  |  | 70 | 44.0542 | -114.839
1994-015-00 | S-42 | Rotary Drum | 18.49 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes | bad concrete -repair |  |  |  | 90 | 44.036 | -114.8343
1994-015-00 | S-43 | Rotary Drum | 27.54 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes | bad concrete -repair + bridge |  |  |  | 100 | 44.0347 | -114.835
1994-015-00 | S-47 | Rotary Drum | 7.4 | IDFG | 1997 | BPA, NMFS, IDFG | Upper Salmon River | yes | bad concrete -repair |  |  |  | 70 | 43.9029 | -114.789
2007-399-00 | SBaC-01 | Rotary Drum | 3 | IDFG | 2013 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.3797 | -114.2587
2007-399-00 | SBaC-03 | Rotary Drum | 1 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular |  |  |  | 70 | 44.3817 | -114.2658
2007-399-00 | SBaC-04 | Rotary Drum | 3.6 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes | bottle brush |  |  |  | 70 | 44.3812 | -114.2689
2007-399-00 | SCC-04 | Rotary Drum | 7.4 | IDFG | 2009 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 45.2513 | -113.8642
2007-399-00 | SCC-05 | Rotary Drum | 4.46 | IDFG | 2009 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular- access problem / bridge |  |  |  | 70 | 45.2552 | -113.8588
2007-399-00 | SCC-06 | Rotary Drum | 18.49 | IDFG | 2009 | BPA, NMFS, IDFG | Upper Salmon River | yes | bridge |  |  |  | 90 | 45.2617 | -113.845
2007-399-00 | SCC-07 | Rotary Drum | 3.2 | IDFG | 2010 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular |  |  |  | 70 | 45.2656 | -113.8326
2007-399-00 | SCC-08,9 | Rotary Drum | 14.79 | IDFG | 2009 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 45.2702 | -113.8265
2007-399-00 | SCC-10/11 | Rotary Drum | 12.24 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes | drop well |  |  |  | 90 | 45.2859 | -113.8154
2007-399-00 | SCC-12 | Rotary Drum | 6.12 | IDFG | 2012 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 45.2944 | -111.8074
2007-399-00 | SCC-13 | Rotary Drum | 7.4 | IDFG | 2013 | BPA, NMFS, IDFG | Upper Salmon River | yes | siphon |  |  |  | 70 | 45.3038 | -113.8033
2007-399-00 | SCC-14 | Rotary Drum | 15.3 | IDFG | 2012 | BPA, NMFS, IDFG | Upper Salmon River | yes | access - egress difficult |  |  |  | 90 | 45.3124 | -113.8042
2007-399-00 | SCCFC-01 | Rotary Drum | 12.24 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 45.2784 | -113.8128
2007-399-00 | SCCFC-02 | Rotary Drum | 3.56 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular - diversion ditch problem |  |  |  | 70 | 45.2788 | -113.7959
2007-399-00 | SCCFC-03 | Rotary Drum | 3.56 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular |  |  |  | 70 | 45.2791 | -113.7819
1994-015-00 | SChaC-02 | Rotary Drum | 7.4 | IDFG | 2005 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.5691 | -114.2018
1994-015-00 | SChaC-03 | Rotary Drum | 9.24 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | Gamache maintains |  |  |  | 70 | 44.5909 | -114.2271
1994-015-00 | SChaC-04 | Rotary Drum | 4.46 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes | wiper |  |  |  | 70 | 44.562 | -114.2424
1994-015-00 | SChaC-08 | Rotary Drum | 60.69 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | Obermeyer weir problem |  |  |  | 140 | 44.5604 | -114.272
1994-015-00 | SChaC-08A | Rotary Drum | 1 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | bottle brush -Obermeyer weir problem |  |  |  | 70 | 44.5607 | -114.2722
1994-015-00 | SChaC-09 | Rotary Drum | 3.57 | IDFG | 2003 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.5719 | -114.3036
1994-015-00 | SChaC-11 | Rotary Drum | 2.68 | IDFG | 2005 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep /maintained primarilly by irrigator / bridge |  |  |  | 70 | 44.5733 | -114.37
1994-015-00 | SChaC-13 | Rotary Drum | 2.68 | IDFG | 2005 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep /maintained primarilly by irrigator / bridge |  |  |  | 70 | 44.5727 | -114.3536
1994-015-00 | SChC-01 | Rotary Drum | 3.57 | IDFG | 2003 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.0162 | -114.813
1994-015-00 | SChC-02/5 | Rotary Drum | 9.18 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | silt |  |  |  | 70 | 44.0143 | -114.7896
2007-399-00 | SChC-03/4 | Rotary Drum | 15.3 | IDFG | 2007 | BPA, NMFS, IDFG | Upper Salmon River | yes | silt |  |  |  | 90 | 44.014 | -114.7828
2007-399-00 | SCoC-01 | Rotary Drum | 3.57 | IDFG | 2011 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.7395 | -113.9995
1994-015-00 | SEF-03 | Rotary Drum | 22.19 | IDFG | 1995 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 90 | 44.2135 | -114.2795
1994-015-00 | SEF-04 | Rotary Drum | 27.73 | IDFG | 2001 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 100 | 44.1985 | -114.2888
1994-015-00 | SEF-05 | Rotary Drum | 7.65 | IDFG | 1995 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 70 | 44.1813 | -114.2864
1994-015-00 | SEF-06 | Rotary Drum | 2.68 | IDFG | 1998 | BPA, NMFS, IDFG | East Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.1791 | -114.285
1994-015-00 | SEF-07/08 | Rotary Drum | 15.3 | IDFG | 1997 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 90 | 44.1518 | -114.303
1994-015-00 | SEF-09 | Rotary Drum | 6.12 | IDFG | 1996 | BPA, NMFS, IDFG | East Fork Salmon River | yes | gravel problem - check bypass |  |  |  | 70 | 44.144 | -114.3233
1994-015-00 | SEF-10/11 | Rotary Drum | 15.3 | IDFG | 2001 | BPA, NMFS, IDFG | East Fork Salmon River | yes | heavy silt, bypass |  |  |  | 90 | 44.1457 | -114.3907
1994-015-00 | SEF-12 | Rotary Drum | 15.3 | IDFG | 1995 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 90 | 44.1467 | -114.3765
2007-399-00 | SEF-14 | Rotary Drum | 9.24 | IDFG | 2007 | BPA, NMFS, IDFG | East Fork Salmon River | yes | access - |  |  |  | 70 | 44.1394 | -114.4008
1994-015-00 | SEF-17 | Rotary Drum | 12.24 | IDFG | 2005 | BPA, NMFS, IDFG | East Fork Salmon River | yes | new screen or drums for consolidation with 15 |  |  |  | 90 | 44.1234 | -114.4248
1994-015-00 | SEF-18 | Rotary Drum | 6.12 | IDFG | 2005 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 70 | 44.1074 | -114.437
1994-015-00 | SEF-18A | Rotary Drum | 6.12 | IDFG | 2002 | BPA, NMFS, IDFG | East Fork Salmon River | yes |  |  |  |  | 70 | 44.0927 | -114.4417
1994-015-00 | SEF-19 | Rotary Drum | 3.57 | IDFG | 2001 | BPA, NMFS, IDFG | East Fork Salmon River | yes | recently replaced with modular |  |  |  | 70 | 44.0803 | -114.4537
1994-015-00 | SEF-21 | Rotary Drum | 2.3 | IDFG | 1996 | BPA, NMFS, IDFG | East Fork Salmon River | yes | drum length = exempt from angle/sweep bridge |  |  |  | 70 | 44.0607 | -114.4607
1994-015-00 | SEFBBC-01 | Rotary Drum | 5.55 | IDFG | 2003 | BPA, NMFS, IDFG | East Fork Salmon River | yes | small drums- rough bypass |  |  |  | 70 | 44.117 | -114.4373
1994-015-00 | SEFBBC-02 | Rotary Drum | 11.09 | IDFG | 2003 | BPA, NMFS, IDFG | East Fork Salmon River | yes | small drums- bypass outlet access |  |  |  | 90 | 44.1141 | -114.438
1994-015-00 | SEFGC-01 | Rotary Drum | 3.57 | IDFG | 1996 | BPA, NMFS, IDFG | East Fork Salmon River | yes | modular |  |  |  | 70 | 44.0398 | -114.4617
1994-015-00 | SEFHC-01 | Rotary Drum | 4.46 | IDFG | 1996 | BPA, NMFS, IDFG | East Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.1542 | -114.3003
1994-015-00 | SEFHC-02 | Rotary Drum | 4.46 | IDFG | 1996 | BPA, NMFS, IDFG | East Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.1498 | -114.2952
1994-015-00 | SEFHC-03 | Rotary Drum | 9.24 | IDFG | 2001 | BPA, NMFS, IDFG | East Fork Salmon River | yes | very difficult access |  |  |  | 70 | 44.11 | -114.259
1994-015-00 | SFJC-01 | Rotary Drum | 7.4 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes | gravel problem |  |  |  | 70 | 44.0299 | -114.8297
1994-015-00 | SFJC-02 | Rotary Drum | 6.12 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes | very difficult access |  |  |  | 70 | 44.0292 | -114.8015
1994-015-00 | SFJC-03 | Rotary Drum | 9.69 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 44.0413 | -114.7583
1994-015-00 | SGC-01 | Rotary Drum | 1 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes | passive |  |  |  | 70 | 44.108 | -114.862
1994-015-00 | SGC-02/3 | Rotary Drum | 4.46 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.1079 | -114.8548
1994-015-00 | SGC-04 | Rotary Drum | 2.68 | IDFG | 2003 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.1191 | -114.8443
1994-015-00 | SIC-08 | Rotary Drum | 6.12 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.9139 | -114.044
1994-015-00 | SIC-09 | Rotary Drum | 1.72 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular drum length = exempt from angle/sweep |  |  |  | 70 | 44.919 | -114.0492
2007-399-00 | SLyC-01 | Rotary Drum | 1.5 | IDFG | 2012 | BPA, NMFS, IDFG | Upper Salmon River | yes | bottle brush |  |  |  | 70 | 44.3238 | -114.2973
1994-015-00 | SMC-01/03 | Rotary Drum | 9.24 | IDFG | 2002 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.6137 | -114.1725
1994-015-00 | SMC-04/05 | Rotary Drum | 4.85 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.6208 | -114.1816
1994-015-00 | SMC-06 | Rotary Drum | 6.06 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes | small bridge |  |  |  | 70 | 44.6272 | -114.1888
1994-015-00 | SMFLCCC-01 | Pump Screen | 0.5 | IDFG | 1997 | BPA, NMFS, IDFG | Middle Fork Salmon River | yes | infiltration system |  |  |  | 70 | 44.8018 | -114.8037
2007-399-00 | SMFLCMC-01 | Rotary Drum | 1.5 | IDFG | 2013 | BPA, NMFS, IDFG | Middle Fork Salmon River | yes | bottle brush |  |  |  | 70 | 44.5424 | -114.8424
2007-399-00 | SMFMCKC-01 | Rotary Drum | 6.12 | IDFG | 2007 | BPA, NMFS, IDFG | Middle Fork Salmon River | yes |  |  |  |  | 70 | 44.3748 | -115.1094
2007-399-00 | SMFMCKC-02 | Rotary Drum | 4.59 | IDFG | 2007 | BPA, NMFS, IDFG | Middle Fork Salmon River | yes |  |  |  |  | 70 | 44.3787 | -115.1057
1994-015-00 | SNF-03 | Rotary Drum | 3.57 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.433 | -113.9918
1994-015-00 | SNF-03A | Rotary Drum | 3.83 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes |  |  |  |  | 70 | 45.4538 | -113.9921
1994-015-00 | SNF-04/5 | Rotary Drum | 6.12 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes |  |  |  |  | 70 | 45.4686 | -113.9912
1994-015-00 | SNF-06 | Rotary Drum | 6.12 | IDFG | 1996 | BPA, NMFS, IDFG | North Fork Salmon River | yes |  |  |  |  | 70 | 45.4853 | -113.9801
1994-015-00 | SNF-06A | Rotary Drum | 3.57 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.487 | -113.977
1994-015-00 | SNF-07 | Rotary Drum | 4.46 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep bridge |  |  |  | 70 | 45.4896 | -113.9719
1994-015-00 | SNF-08 | Rotary Drum | 3.57 | IDFG | 1996 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep bridge |  |  |  | 70 | 45.5115 | -113.9396
1994-015-00 | SNF-09 | Rotary Drum | 3.57 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.5279 | -113.9342
1994-015-00 | SNF-11 | Rotary Drum | 2.3 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.5478 | -113.9348
1994-015-00 | SNF-13 | Rotary Drum | 2.3 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 45.5599 | -113.9457
1994-015-00 | SNFDC-01 | Rotary Drum | 6.12 | IDFG | 1996 | BPA, NMFS, IDFG | North Fork Salmon River | yes |  |  |  |  | 70 | 45.5391 | -113.9284
1994-015-00 | SNFSC-01 | Rotary Drum | 15.3 | IDFG | 1995 | BPA, NMFS, IDFG | North Fork Salmon River | yes | gravel |  |  |  | 90 | 45.7003 | -113.9494
2007-399-00 | SPoiC-01 | Rotary Drum | 3.57 | IDFG | 2014 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.8796 | -113.9475
1994-015-00 | SSC-01 | Rotary Drum | 12.24 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes | heavy gravel/silt problem |  |  |  | 90 | 44.258 | -114.4584
1994-015-00 | SSC-02 | Rotary Drum | 4 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | flat plate wiper |  |  |  | 70 | 44.2617 | -114.46
1994-015-00 | SSC-04 | Rotary Drum | 3.57 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.2802 | -114.4674
1994-015-00 | SSC-05 | Rotary Drum | 2.68 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.2933 | -114.4736
1994-015-00 | SSC-06 | Rotary Drum | 2.68 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.2984 | -114.4754
1994-015-00 | SSmC-01 | Rotary Drum | 4.59 | IDFG | 2006 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 43.907 | -114.7989
1994-015-00 | STMC-02 | Rotary Drum | 2.53 | IDFG | 2004 | BPA, NMFS, IDFG | Upper Salmon River | yes | wiper - solar / rebuild POD |  |  |  | 70 | 45.0112 | -113.9179
2007-399-00 | SToC-03 | Rotary Drum | 2 | IDFG | 2013 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 45.3253 | -113.8895
1994-015-00 | SVC-01 | Rotary Drum | 9.24 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | concrete floors bad - need repair |  |  |  | 70 | 44.2715 | -115.0067
1994-015-00 | SVC-02/03 | Rotary Drum | 9.24 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | concrete floors bad - need repair |  |  |  | 70 | 44.2883 | -115.0127
1994-015-00 | SVC-04 | Rotary Drum | 7.4 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | concrete floors bad - need repair |  |  |  | 70 | 44.2895 | -115.0141
1994-015-00 | SVC-05/06 | Rotary Drum | 12.24 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | concrete floors bad - need repair |  |  |  | 90 | 44.3102 | -115.0546
1994-015-00 | SVCEC-01 | Rotary Drum | 9.24 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | concrete floors bad - need repair |  |  |  | 70 | 44.2904 | -115.0274
2007-399-00 | SVCGC-06,07 | Rotary Drum | 18.49 | IDFG | 2009 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 90 | 44.2003 | -114.9719
1994-015-00 | SVCIC-02 | Rotary Drum | 2.68 | IDFG | 2005 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.2211 | -114.9624
1994-015-00 | SVCIC-03 | Rotary Drum | 3.57 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes | drum length = exempt from angle/sweep |  |  |  | 70 | 44.2158 | -114.9704
1994-015-00 | SVCIC-04/05 | Rotary Drum | 9.24 | IDFG | 2001 | BPA, NMFS, IDFG | Upper Salmon River | yes |  |  |  |  | 70 | 44.2138 | -114.9791
2007-399-00 | SVCIC-07 | Rotary Drum |  | IDFG | 2007 | BPA, NMFS, IDFG | Upper Salmon River | yes | bottle brush - paddle powered |  |  |  | 70 | 44.212 | -114.98
1994-015-00 | SVCSLC-01 | Rotary Drum | 3.57 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular drum length = exempt from angle/sweep |  |  |  | 70 | 44.2587 | -115.0257
1994-015-00 | SWC-01 | Rotary Drum | 3.57 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular drum length = exempt from angle/sweep Warm Creek |  |  |  | 70 | 44.0013 | -114.8269
1994-015-00 | SWmC-01 | Rotary Drum | 1 | IDFG | 2000 | BPA, NMFS, IDFG | Upper Salmon River | yes | passive perf plate |  |  |  | 70 | 44.0979 | -114.8579
1994-015-00 | SWmC-02/03 | Rotary Drum | 7.4 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | Upper Salmon Williams Creek |  |  |  | 70 | 44.0943 | -114.8465
1994-015-00 | SWmC-04 | Rotary Drum | 3.57 | IDFG | 1999 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular -drum length = exempt from angle/sweep Upper Salmon Williams Creek |  |  |  | 70 | 44.0945 | -114.8455
1994-015-00 | SWSC-01 | Rotary Drum | 3.57 | IDFG | 1998 | BPA, NMFS, IDFG | Upper Salmon River | yes | modular -drum length = exempt from angle/sweep Warm Springs Creek irrigator maintained |  |  |  | 70 | 44.2541 | -114.6754